## Slide 1
Estimating Best Practices
CPARB
04/14/2022
The background fill can also be changed to an image. (Right click on the slide and select “Format Background…”)

## Slide 2: AE Fees/Agency PM Fees
What we found/heard
Fee percentages for basic services are too low
Hourly rates are too low
Fee structures do not reflect alternative delivery
Projects are using “other services” to increase fees – often substantially
Inconsistency in what counts as “other services”
Not all C-100s report the “total project cost”, some agencies report budget funding per biennium, percentages are not clear

## Slide 3: AE Fees/Agency PM Fees
Impact
The result is a lack of consistency or transparency across projects, and some high overall fee percentages

## Slide 4: AE Fees/Agency PM Fees
Proposals
Revise the fee tables and hourly rates
Add Alternative Delivery
  Design Build – (3 types – performance, bridging, progressive)
  GC/CM
Monitor total design/management fees on total project aside from allocation between AE/Contractor/Agency
Improve definition of “Basic” and “Other” services

## Slide 5: Escalation
What we found/heard
Current escalation is extremely high and erratic
C-100 rates are missing badly – budgets are set too early to be meaningful in volatile times
Global Insight is a national “input cost” index – does not cover market issues
“Code & Practice” escalation is not always being addressed by sponsors
Many projects are managing – either by reducing scope or finding extra money
Many projects are significantly impacted
Some projects appear to be managing well

## Slide 6: Escalation
Proposals
Keep the current escalation metric as a baseline for C-100
Consider market specific modifiers: location, demand, market response, scale
Consider an alternative index for civil/horizontal projects
Make sure that “Code & Practice” escalation is addressed by project sponsors through a specific line on the C-100
Encourage project sponsors to undertake project specific escalation/market/code assessment

## Slide 7: Contingency
What we found/heard
Contingency allowances need to have more flexibility
Projects seem to be managing by including allowances in the C-100
Projects seem to be managing by adjusting scope and moving funds within budgets

## Slide 8: Contingency
Proposals
Make contingencies explicit and transparent
Encourage project sponsors to undertake project specific risk assessments to substantiate any change in contingency. Assessments do not need to be full risk workshops

## Slide 9: Life Cycle Costing
What we found/heard
Multiple LCC requirements are confusing
LCC is still an afterthought on some projects – and not seen as a core budgeting process
Proposals
Streamline the LCC tools
Link with Value Engineering
Consider requiring Total Cost of Ownership as a field in C-100

## Slide 10: Value Engineering
What we found/heard
VE is still an afterthought on some projects – and not seen as a core budgeting process
Proposals
Embed scale appropriate VE into the projects, both at concept (Value Analysis) and during design
Link with LCC

## Slide 11: Transparency/Controls
What we found/heard
C-100 is effective for current budget uses
It has been modified and adapted by some users
It does not provide for good comparison/data analysis/transparency
Users feel it is too focused on conventional delivery
Not matched to the scale or nature of all projects (parks)
The set “controls” (fee schedule, contingency, scope breakdown) are not effective as controls

## Slide 12: Transparency/Controls
Proposals
Modify the C-100 structure
  Keep rows consistent – at least at subtotals
  Improve consistency on “typical” modifications
Include a “total project” cost – even where the funding request is only for one phase
Improve linking to actual expenditures
Use project scale thresholds for specific policy requirements